## PO7.4 Professionali
CeIS Roma |  | Procedura Operativa 7.4 | [7 empty] | cod. doc. FLU74.02
|  | Approvvigionamento delle prestazioni professionali | [7 empty] | rev. 0
Centro Italiano di Solidarietà
N° | AZIONE |  | Responsabile |  |  |  |  | Riferimenti | Documentazione
|  |  | DG | DP | UPE | RP | RGQ
1 | Individuazione di potenziali fornitori |  | 1 | 1 |  | 1 |  | PO7.4: 4.1.2 e 4.2.2 Att. 10 | Richiesta valutazione nuovo fornitore
2 | Valutazone e qualificazione nuovi fornitori |  | 2 |  | 2 |  |  | PO7.4: 4.2.2 Att.20 e 30 | MOD74.05 (Scheda qualificazione fornitore di prestazioni professionali) Sezioni A+B+C+D
3 | Formulazione del giudizio finale |  | 3 | 3 | 3 |  | 3 | PO7.4: 4.2.2 Att.20 e 40 | MOD74.05 (Scheda qualificazione fornitore di prestazioni professionali) Frequenza valutazione successive
6 | Valutazione continua dei fornitori |  |  |  | 4 |  |  | PO7.4: 4.2.2 Att.20 e 50 | MOD74.06 (Valutazione e qualificazione continua dei fornitori delle prestazioni professionali) Sezioni A+B+C+D+E
7 | Formulazione del giudizio finale |  | 5 | 5 | 5 |  | 5 | PO7.4: 4.2.2 Att.20 e 60 | MOD74.06 (Valutazione e qualificazione continua dei fornitori delle prestazioni professionali) Frequenza valutazione successive
8 | Aggiornamento elenco fornitori |  |  |  | 6 |  |  | PO7.4: 4.2.2 Att.70 | MOD74.07 (Elenco / Scheda fornitori di prestazioni professionali

## Macro-flow
Fase 1° - Project Selection | Fase 2° - Project Proposal | Fase 3° - Project Implementation | Fase 4° - Project Evaluation | Fase 5° - Project Closure
Identification of funding opportunities (PO7.2)
Criteria based selection of funding opportunities (PO7.2)
Nomination of project planning team (PO7.2) | Preparation of project development plan (PO7.3)
Preparation of project, including staffing, equipment and resources (PO7.3)
Validation, final analysis and check of completeness (PO7.3)
| Submission of project proposal (PO7.2) | Evaluation and acquisition of personnel, products and services (PO7.4)
Project implementation, with 3 monthly reviews and modifications where necessary (PO7.5)
|  | Survey of stakeholder and beneficiary satisfaction, annual evaluation and preparation of quality improvement objectives for the next year (PO7.2) | Evaluation of the degree of learning/improvement, level of satisfaction of stakeholders and beneficiaries and the effectiveness of the project against its objectives (PO7.5 & 7.2)
Preparation of final (or annual) report for funder(s) and publication of appropriate project documents (PO7.2 & PO7.5)